Second progress Report

Developing Strategic Alliances with National, Regional and International Institutions

Prepared for

Office of Planning & Quality

King Fahd University of Petroleum & Minerals

Dhahran, Saudi Arabia

Prepared by

Dr. Faizur Rahman

Dr. Sadiq M. Sait

Dr. Saeid A. Al-Ghamdi

Dr. Ibnelwaleed A. Hussien

D’Qada 1427 H

December 2006 G

summary

This is the Second Progress Report of the study titled “Developing Strategic Alliances with National, Regional and International Institutions” conducted for the Office of Planning & Quality, KFUPM. The study was initiated on 01 March 2006. The objectives of the study are to identify areas of sustainable cooperation and strategic alliances with member institutions to enhance teaching and research as well as develop a plan, and policies and procedures, to facilitate interaction and collaboration with member institutions on sustained basis.

The project activities were initiated by assessing the current status of collaborations at KFUPM.  Contacts have been made with heads of all the KFUPM academic departments and Research Institute Centers, relevant key members of KFUPM such as Supervisor, Dhahran Techno Valley, Director, Office of International Cooperation and others.  A questionnaire was prepared and circulated to all the department heads and faculty to obtain input on existing collaborations and suggestions on developing new strategic alliances in research and education.  Contacts are being made with industry and other national institutions to determine the areas of high research priority.  Criteria for selection of suitable institutions for developing strategic alliances are being formulated.  In-house documents and literature from other universities related to policies and procedures have been reviewed.

Preliminary findings indicate that no student exchange programs exist with external institutions. Collaborations with national universities are almost non-existent and no office is available at KFUPM to handle national collaborations.  It is observed that international collaborations exist in some departments, but mostly on an individual basis.

The response from department heads and faculty members on questionnaire circulated is found to be very weak.  Significant follow up is required to acquire necessary information and data.  The team will continue to work on various tasks as per the schedule.  A workshop is planned to be organized in early November 2006.

Table of Contents

Title		page

1	Introduction

2	Objectives of the Study

3	Methodology

4	Tasks completed

4.1	Present Status

4.1.1	Existing Areas of Research Excellence

Multi-disciplinary Areas (using Faculty Survey)

Research Areas by Department (using Faculty Survey)

4.1.2	Existing Relationship with External Institutions

National Institutions

International Institutions

4.2	Define Strategic Areas of Cooperation

4.2.1	Identify National Research Needs

Input from KFUPM

Faculty Survey

Interviews (Chairmen, Deans)

Focus Groups

Input from Industry

Aramco

SABIC

STC

SEC

KACST

MOHE

    - New Areas in Line with International Trends

Input from KFUPM

4.2.3	Research Directions

4.3	Proposed National and International Collaborations

4.3.1	National Institutions for Collaborations

Collaboration in Research

Collaboration in Teaching/Learning (including short courses)

4.3.2	International Institutions for Collaboration

Collaboration in Research

Collaboration in Teaching/Learning (including short courses)

Research Consortia (National/International) to work on research

topics of strategic importance

4.4	Develop Plan, Policies and Procedures

5	significant findings

6	recommendations

  - Recommendations and initiatives to realize the recommendations.

  - An action plan to implement each initiative.

  - The action plan is an implementation plan that specifies tasks, resources needed, responsibilities and time frame.

  - Measures to monitor the impact of the initiatives.

7	Problems and Concerns

8	Future Plan

Appendices

Appendix – A

Appendix – B

Appendix – C

Appendix – D

1	Introduction

This is the Second Progress Report of the study titled “Developing Strategic Alliances with National, Regional and International Institutions” conducted for the Office of Planning & Quality, KFUPM. The study was initiated on 01 March 2006. The project activities during the period September /October 2006 are reported in this progress report.

Linking advances in science and engineering with their potential uses is invariably multi-dimensional and interdisciplinary and often needs exchange of knowledge, information, and technologies. These linkages accelerate innovation, often yielding new insights into the underlying research.  Many Universities now recommend working together to develop broad research and educational alliances with various potential institutions.  This study is therefore, undertaken to develop alliances in strategic areas of research and education with national as well as international universities and institutions. The approach adopted in this study, and the preliminary findings, are described in the following sections.

2	objectives of the study

The aim of the project is to develop and maintain effective and sustainable collaboration with national, regional and international institutions of choice to enhance teaching and research.

The specific objectives of the study are:

- Identify areas of sustainable cooperation and strategic alliances with member institutions to enhance teaching and research.

- Develop a plan, and policies and procedures to facilitate interaction and collaboration with member institutions.

A bar chart showing the project schedule is given in Figure 1.  The project has started on 01 March 2006.  The project duration is 12 working months excluding annual vacation and Eid Holidays.  The project will be completed by end of May 2007.

Figure 6.1 Proposed Project Schedule

(Project Duration: 12 working months excluding annual vacation and Eid Holidays)

Project start date; 01 March 2006		Project end date: 30 May 2007

3	Methodology

The primary objective of this study is to develop a plan to establish meaningful relationships between KFUPM and other key national, regional and reputable international institutions.  Comprehensive surveys are being conducted by contacting faculty members within KFUPM and nation-wide, major industries, and research organizations to define key research areas of national priority.  The study is divided into the following four major tasks.

Task 1.	Assess Current Level of Relationship

Task 2.	Define Strategic Areas of Cooperation

Task 3.	Select Institutions for Cooperation

Task 4.	Develop, Plan Policies and Procedures

A comprehensive literature search and review was carried out and reported in the first progress report.  The information on current areas of cooperation in terms of education and research is being collected by preparing a questionnaire and circulating it to the following stakeholders at KFUPM.

- All Deans

- Chairmen and faculty members of all Academic Departments

- Supervisor, Dhahran Techno Valley

- Center Directors of Research Institute

- Office of International Cooperation

- Chairman, Science Park

- Director, Innovation Center

The questionnaire is enclosed in Appendix A. Information is being collected on current level of interactions, collaborations, existing memoranda of understanding and agreements between KFUPM and other national, regional and international universities and institutions.  Existing and proposed research areas are being compiled from all the stakeholders.

4	MAJOR Achievements

The status of various tasks and significant findings during the last two months are described in the following sub-sections.  The response from the stakeholders is very poor and even after repeated reminders no improvement was recorded.  The input from faculty members and chairmen is necessary for the completion of the various tasks and success of this project.  The input received from very few faculty members and chairmen is presented in the following sections.

4.1	Task Completed

- Task 1. Assess Current Status

The assessment of current status about collaborations in research and teaching has been compiled from the on-line survey designed, and administered by the project team.

  - The chairman of following 7 departments did not provide any response yet to the questionnaire.  Some of them indicated that the questionnaire is too long to be filled.

    - Management Information System & Accounting (MISAC)

    - Finance & Economics Department  (FINEC)

    - Management & Marketing Department  (MGMK)

    - Architectural Engineering Department  (ARE)

    - Architecture Department  (ARC)

    - City & Regional Planning Department (CRP)

    - Construction Engineering & Management Department  (CEM)

    - Electrical Engineering Department  (EE)

  - Interviews of few department heads have been carried out to obtain relevant information and data.  It is noticed that interviews are providing valuable information and discussions are leading to generate new ideas.

The current status of strategic alliances at the various academic departments is presented and tabulated in Appendix B.  A summary of the number of filled forms categorized by the colleges of the University, the current areas of research and status of current collaborations is presented in Appendix B.  The current status shows sporadic endeavors and on individualized basis that lack synergy and momentum for sustainability and/or continuity for a pre-defined span of time with well-defined objectives.

Additional data is still being compiled and the information is updated.  It is decided by the project team to collect necessary information by arranging interviews with department chairmen and utilizing RA’s to interview selected faculty members.  This task is now in progress.

- Task 2. Define Strategic Areas of Cooperation

Task 2 is in progress and data have been compiled and reviewed from the following sources:

- Input from faculty members and other stakeholders through questionnaire

- Input from Industry (Saudi Aramco, SABIC, SEC, STC, SWCC)

- KACST Technology Plan and Comprehensive National Plan for Science & Technology prepared by Ministry of Higher Education for year 2007 to 2010.

The relevant information on research areas of high priority that addresses national needs as well as new emerging technologies were acquired through different sources mentioned above.  The input from the KFUPM faculty on research areas are presented in Appendix C.  Major industries were contacted or their input was taken from relevant documents that indicate their research requirements.

Industry input in Appendix D

The priority research areas for Saudi Arabia extracted from KACST S&T plan and Ministry of Higher Education is presented Appendix E.

  - Identified industry needs by contacting major industries and reviewed their web sites.  This task is in progress.

  - A preliminary list has been prepared on areas of research priority based on input from all the stakeholders received so far.  The list will be revised when all the information and data is acquired from stakeholders.

Research Directions based on Report of the KFUPM Committee on Areas of Research Concentration for Saudi Society

  - Oil & gas,

  - Water,

  - Electric energy,

  - Material science and metrology, and

  - Maintenance operations

- Task 3. Select Suitable Institutions for Collaboration

In Task 3, the team has prepared a list of potential institutions for collaborations in the areas of mutual interest based on the input provided by the faculty members through survey. Criteria has been formulated to select institutions/consortia based on priority research areas and mutual benefits that will be sustainable.  The list of institutions indicated by faculty members is tabulated in Appendix F

A list of universities with whom MOU has been signed is acquired from OIC and is attached in Appendix-G.  However, it is indicated that the implementation plan is not defined adequately.

- Task 4. Develop Plan, Policies & Procedures

Task 4 is given low priority at present and preliminary information on policies and procedures is being compiled.

4.2	Significant Findings

The project team reviewed the data acquired through different sources.  Some preliminary findings based on the analysis of the data and information received so far is presented in the following paragraphs.

- Current Status

Existing relationship with other institutions

  - Teaching

    - No student exchange programs/agreements.

    - Faculty exchange program through British Council/JCCP exist to some extent.

    - Visiting faculty in some departments is active.

    - No agreements on short courses with national/international institutions.

  - Research

    - Limited national collaborations on individual faculty basis but no formal agreements exist between institutions other than KACST.  There is no office to handle collaborations with national universities.

    - Few international collaborations (Ciba, JCCP, Intel, Schlumberger, British Aerospace, . . .) and some cases are under discussion (Microsoft, Hydro-Kobeco, Yokogawa,  . . . ).

Existing areas of research excellence

  - Academic Departments

    - Few satisfy national needs and linked with industry.

    - Most of them related to basic research or applied research not relevant to national needs.

    - Innovative research in some departments is on-going.

    - No clearly defined research directions by Research Committee at present.

  - Research Institute

    - Four Centers of Research Institute are linked to industry.

    - Mainly services and trouble shooting.

    - Some novel and developmental work is undertaken.

- Strategic Areas of Cooperation

Research Areas of National Needs

    - Identified research topics based on

      - Input from departments,

      - KACST S&T  Plan, and

        - Water, Exploration, Refining, petrochemicals, mining, IT, New materials, Aerospace, Bio-technology, Building & Construction, environment etc.

      - Input from industry.

    - Priority Research Areas

      - Plan to select two research areas per department based on national needs and existing areas of excellence in the department.  This will be done in consultation with Department head.

Areas of Cooperation in Teaching

    - Identified avenues of cooperation in teaching/learning mainly: faculty/students exchange programs, short courses, research training, seminars on special topics and visiting faculty.

- No Office to handle National Collaborations

Suggested to establish:

Office of External Cooperation

      - International Division

      - National Division

5	obstacles

The project is running smooth with all the team members participating actively.  The project team is experiencing however, some problems which are as follows:

        - Delay in response on questionnaire from stakeholders (Faculty, Department Heads, Industry) will affect the timely completion of the tasks I, II and III.

        - Significant follow up is required to obtain the data from stakeholders which is basically consuming more time than expected from each team member.

        - It is felt necessary to involve a Consultant for handling legal procedures in formulating policies and procedures for establishing partnership agreements.  The team is suggesting involving a faculty member who is experienced in preparing legal agreements.

        - Some project activities are overlapping with OIC activities and it is suggested by the team members to work in close coordination with OIC, office.

6	recommendations

- . Must  include

  - Recommendations and initiatives to realize the recommendations.

  - An action plan to implement each initiative.

  - The action plan is an implementation plan that specifies tasks, resources needed, responsibilities and time frame.

  - Measures to monitor the impact of the initiatives.

7	Future Plan

The project team discussed the issue rigorously and decided to collect the information by personally visiting selected faculty members and visiting all chairmen.

The team members are not working during summer.  The project activities will be resumed starting from September 2006.  The planned activities are as follows:

  - Complete Task 1 (expected within two months)

  - Continue Tasks 2, 3 and 4

  - Conduct Interviews and Focus Groups

  - Organize a Workshop in October/November 2006

APPENDIX – A: Questionnaire

Project Title: Developing Strategic Alliances with National, Regional and International Institutions

The aim of the project is to develop and maintain an effective and sustainable collaboration with reputable national, regional and international institutions of higher learning and research centers to enhance teaching processes and research quality & productivity at KFUPM.

Faculty Name

Department  	                         email

1. Please provide information on your existing collaboration(s) with institutions/universities:

  - National

(Saudi Arabia)

  - Regional

(Middle East)

-   International

N. America

EU

Asia, Australia

2. Please indicate the existing areas of research excellence in your department:

- 2)

3)	4)

- 6)

  - According to you, what are the priority research areas of National needs that may benefit from strategic alliance:

1)	2)

3)	4)

- 6)

1.	Institutions: Universities or Research organizations

2.	Regional: Middle East (Neighboring countries like Kuwait, UAE, Oman, Iran, Egypt, Sudan, etc.)

3.		International: N. America, EU, Australia, Asia

4. Specify National, Regional and International Institutions with whom you would like to collaborate to address research in areas of national needs:

  - National Institute

  - Regional Institute

(Middle East)

  - International Institute

(N. America, EU, Asia, …)

  - Suggest new research areas in line with international trends and specify institutions:

| No. | Research Area | Recommended Institutions | Contact Details |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |
| 6. |  |  |  |

  - Propose research consortia between KFUPM and other institutes in selected research areas:

| No. | Research Topic | Member Institutions |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |

Consortium: A cooperative arrangement among group of institutions to invest jointly in a research program and share the results

Please provide Information on Faculty/Student exchange program(s) in your department in collaboration with other universities:

a) Existing

Regional

International

b) Suggested

Regional

International

  - Please provide information on short courses/seminars in your department in collaboration with other universities:

a) Existing

Regional

International

b) Suggested

Regional

International

  - Please provide information on visiting faculty members from other universities in your department:

a) Existing

Regional

International

b) Suggested

Regional

International

9. Any other Comments/Suggestions

Appendix B

Feedback from Various KFUPM Departments on present status of Research areas and existing collaborations

| College | Departments | Number of Feedbacks | Current Active Research Areas | General Status on Currently On-going Strategic Alliances |
| --- | --- | --- | --- | --- |
| Engineering Sciences & Applied Engineering | Civil Engineering | 1 | Computational mechanics (FEM-based automated analysis and design optimization studies of RC and steel structures) RC structures durability studies (experimental & analytical) Analysis and design of problematic soil | Herriot Watt U. –Scotland, UK (Prof. B. Topping). Virginia Poly. Inst.– Blacksburg-VA, USA (Prof. Z. Gurdal & Prof. Ali H. Nayfeh at the Dept. ESM-V. Tech) KACST-Riyadh (Sponsored projects by G. Directorate of Applied Research) KSU-Riyadh joint-cooperation on offering short-courses on earthquake resistant structural designs |
|  | Chemical Engineering | 2 | Polymers & Plastics Catalysis Desalination Refining Corrosion | SABIC Saudi ARAMCO |
|  | Aerospace Engineering | 1 | Flight dynamics & Control Aerodynamics Propulsion Flight Structures | none |
|  | Petroleum Engineering | 1 | Enhanced oil Recovery Petro-physics Gas condensate reservoirs Sand control | Louisiana State University, USA ( Prof. Ali Ghalambor) |
|  | Electrical Engineering | 0 |  |  |
|  | Mechanical Engineering | 0 |  |  |
| Industrial Management | Management & Marketing | 1 | Strategic planning and marketing strategies Organizational development | none |
| Computer Science & Computer Engineering | Computer Engineering | 2 | Digital design automation Encryption and security Robotics Computer Networks VLSI design & Parallel and distributed systems | A University in Tunisia American University-Beirut, Lebanon Florida Inst. Technologies (Dr. T. Kharobi) Int. Islamic U., Malaysia Kuwait U. (Dr. M. El-Barr) |
|  | Systems Engineering | 1 | Maintenance planning & Scheduling Automation and control Quality control Instrumentation | none |
|  | Information & computer Sciences | 3 | Networks & Computer Graphics Software Engineering AI & Multi-media systems Arabization Computational Intelligence in Bioinformatics Machine learning | KSU-KSA Mansura University-Egypt Cornell U.-USA Edinburgh University-UK National University of Singapore |
| Sciences | Mathematical Sciences | 1 | Commutative algebra Wavelets & variational inequalities Differential equations | Short-duration visits from "Universities in South Africa; UK; India; Jordan; Portugal" only to deliver speeches on specific subjects including Algebra-ring theory and differential equations. |
|  | Chemistry | 1 | Catalysis Polymers Corrosion | University of Oman-Muscat; Oman U. Western Ontario-Canada Open University-Cardiff, UK |
|  | Physics | 2 | Surface science Laser physics Superconductivity Thin films Radiation physics Condensed matter theory Nuclear physics | Lawrence Berkeley National Laboratory-CA-USA (Dr. Z. Hussain) National Center for Physics, Islamabad-Pakistan (Prof. Riazuddin) U. Illinois at Urbana-Champaigne-USA ( Prof. M. Nayfeh) Victoria U. –Melbourne-Australia (Prof. D. Booth) Institute of Chemical Process Fundamental-Prague (Prof. J. Pola) Institute of Physical Chemistry, Heildelberg U., Germany (Prof. P. Hess) Two Workshops in Pakistan and short-course on teaching physics offered to high-schools'teachers. |
|  | Earth Sciences | 2 | Exploration seismology Earthquake Seismology Groundwater exploration Geostatistics, regional geology & Hydrogeology | MIT University of Edinburgh-UK Australian National University Sabanci University |
|  | Islamic & Arabic Studies | 1 | Islamic studies & civilizations Terminologies | Kuwait Universty Exeter University-UK Int. Islamic U.-Malaysia |
| Environmental Design | CER | 2 | Power system planning & quality Power distribution system analysis Energy Conservation management Solar Energy Corrosion | KACST |
| Research Institute | Center for engineering research. | 1 | Concrete Durability. Reinforcement corrosion | none |
|  | Center for refining & petrochemicals | 2 | catalysis & kinetics polymer production & degradation petrochemical productions storage batteries | SABIC-Riyadh (Catalysis; Dr. Karim) SABIC (Dr. Atieh) |

Appendix C

Feedback from Various KFUPM Departments on status of Current and proposed areas of Research

| Departments | Inputs | Current Active Research Areas | Proposed Research Areas |
| --- | --- | --- | --- |
| College Engineering Sciences & Applied Engineering |
| Aerospace Engineering | 2 | Flight Dynamics and control Flight Structures Aerodynamics Propulsion | National Priority Material Sciences New Areas & Emerging Technologies Instrumentation and measuring systems Electronics and avionics |
| Civil Engineering | 1 | Computational mechanics (FEM-based automated analysis and design optimization studies of RC and steel structures) RC structures durability studies (experimental & analytical) Analysis and design of problematic soil Structural Health Monitoring (SHM) Self Compacting Concrete Development of New Local Materials Protection of Concrete Materials | National Priority Optimal Design for Structural Durability Structural Dynamics, Control and Optimlization Earthquake Engineering Development of New Local Materials Protection of Concrete Materials New Areas & Emerging Technologies Structural Design for RC Structural Durability |
| Chemical Engineering | 2 | Polymers & Plastics Catalysis Desalination Refining Corrosion Membrane Technology: Fuel cell and filtration membranes Nanotechnology and New Materials | National Priority Desalination Catalysis in Refining & Petrochemicals Corrosion Polymers and plastics Membrane Technology: Fuel cell and filtration membranes New Areas & Emerging Technologies Environment Process Control Nanotechnology and New Materials |
| Electrical Engineering | 1 | Channel coding and modulation Wireless Communication (channel characterization, access techniques) Equalization and adaptive filtering Image processing On line partial discharge diagnostics of cables and cable terminations On line partial discharge diagnostics of Gas Insulated Switchgear (GIS) Distribution network planning incorporating distributed generation Renewable energy - Wind and Solar Industrial applications of electrostatics |  |
| Mechanical Engineering | 1 | Laser machining applications Thermal fluid sciences | National Priority Corrosion Protection Surface coatings applications for gas turbines New Areas & Emerging Technologies Laser Micromachining Surface coatings: Multilayer coatings Nanotechnology |
| Petroleum Engineering | 1 | Enhanced oil Recovery Fluid property correlations Horizontal well performance Petro-physics Gas condensate reservoirs Sand control Petroleum Exploration | National Priority Reservoir simulation Enhanced oil Recovery Carbonate reservoir characterization Tar and heavy oil recovery New Areas & Emerging Technologies |
| College of Computer Science & Computer Engineering |
| Computer Engineering | 2 | Comp Arch & Digital Design Parallel & distributed Systems Communications & Networks Digital design automation Encryption and security Robotics Computer Networks VLSI design & Parallel and distributed systems and automation Computer Applications | National Priority Data/Information Security Computer Networks VLSI design & Parallel and distributed systems and automation Computer Applications Encryption and security New Areas & Emerging Technologies AI and Soft Computing Embedded Systems Modeling, Simulating & Synthesizing VLSI Hardware for Comp Arithmetic |
| Systems Engineering | 1 | Maintenance planning & Scheduling Automation and control Quality control Instrumentation Productivity measurement | National Priority Maintenance planning Instrumentation Hajj Research New Areas & Emerging Technologies Careful discussion with chairman |
| Information & computer Sciences | 3 | Networks & Computer Graphics Software Engineering AI & Multi-media systems Arabization Computational Intelligence in Bioinformatics Machine learning & Data Mining | National Priority Networks & Security Arabization Graphics E-Commerce and web-mining New Areas & Emerging Technologies Intelligent Systems Uncertainty Reasoning Bioinformatics, Nanotechnology |
| College of Sciences |
| Mathematical Sciences | 1 | Commutative algebra Wavelets & variational inequalities Differential equations | National Priority Numerical Analysis New Areas & Emerging Technologies |
| Chemistry | 1 | Catalysis Polymers Corrosion Water Soluble Polymers: Synthesis and characterization Computational chemistry New Materials and Nanotechnology | National Priority Catalysis Polymers Corrosion Nanotechnology Food Chemistry New Areas & Emerging Technologies Nanotechnology Food Chemistry |
| Physics | 2 | Surface science Laser physics Superconductivity Thin films Radiation physics Condensed matter physics Nuclear physics & Medical physics Lasers and their applications | National Priority Nanoscience and technology Catalysis Material science New Areas & Emerging Technologies Nanomaterials and nanotechnology Lasers applications in different fields Catalysis in Petrochemicals wirelless communication optical and Biosensors Non destructive testing techniques optical imaging smart materials |
| Earth Sciences | 2 | Exploration seismology Earthquake Seismology Groundwater exploration Geostatistics, regional geology & Hydrogeology Ground Water Exploration Geohazard Mathematical Geophysics, Inverse Problems, Rock Physics Geophysical Signal Processing, Fractal Models Sedimentary & Petroleum Geology Environmental geology | National Priority Hydrogeology and groundwater resources Hydrocarbon prospecting Earthquake Seismology Geology of SaudiArabia MineralDeposits Oil-Induced Seismic Hazard Experimental Geophysics Enviromental Disaster Preventing and Mitigation Mineral Deposits New Areas & Emerging Technologies Earthquake Forecasting water resources Geostatistics and gelogic modeling Active Fault Research seismic exploration IsotopeGeology,MIneralogy Ground Motion |
| Islamic & Arabic Studies | 1 | Islamic studies & civilizations Profession Ethics Financial Transactions Terminologies Communication Skills | National Priority Islamic studies & civilizations Profession Ethics Financial Transactions Terminologies Communication Skills New Areas & Emerging Technologies Profession Ethics Financial Transactions Islamic Committees in Banks |
| College of Environmental Design |
| CP | 0 |  | National Priority New Areas & Emerging Technologies |
| Research Institute |
| Center for Engineering Research. | 4 | Concrete Durability. Reinforcement corrosion Wind energy Solar Energy Corrosion Power system planning & quality Power distribution system analysis Energy Conservation management High voltage Power and Distribution System Analysis Building Materials Pavement Research Materials Characterization | National Priority Sand Movement Restructure of Power Systems & power quality Energy Conservation & management High voltage Renewable Energies & photovoltaic cells Life assessment of Mechanical Components Corrosion, Building Materials Pavement Research New Areas & Emerging Technologies Nano-technology Multi-disciplinary groups to cater the needs of industry Flow Induced Vibration |
| Center for Refining & Petrochemicals | 3 | catalysis & kinetics Petroleum Refining Processes polymer production & degradation petrochemical productions storage batteries Scale control chemicals for desalination plants and oil wells | National Priority Petroleum Refining Gas Processing Polymers and plastics Novel chemicals to prevent scaling in desalination plants and oil wells New Areas & Emerging Technologies Integration of Petroleum Refining and Petrochemicals Industry |
| Industrial Management |
| Management & Marketing | 1 | Strategic planning Marketing strategies Cross Cultural Studies Organizational development | National Priority Management development programs Quality management Management consultation productivity studies |
| Dhahran Techno Valley |
| KASP | 1 |  |  |

Appendix D

Research Directions – Input from Industry

Saudi Aramco

The main research topics suggested by Saudi Aramco R & D Department are as follows:

1. Novel Catalysts for Refining Processes

2. Oil Exploration and Drilling Technologies

3. Enhanced Oil Recovery

4. Carbon Management

5. Liquid hydrocarbons to Hydrogen

6. Petroleum Combustion

7. Clean Fuel Technologies

8. Oil to petrochemicals and chemicals

Saudi Electric Company (SEC)

The broad general topics can be considered to be under the following heads.

1. Power Quality

2. Electric Energy Conservation

3. Biological Effect of Power Frequency Electromagnetic Fields

4. Power System Equipment Failure Analysis

Further specific areas of research in which universities are working with SEC and Ministry of Water & Electricity are:

- Power system transients

- Power quality

- Insulator contamination studies

- Power system equipment failure analysis

- Distribution system evaluation and analysis

- Demand side management

- Electric energy conservation

- Generation capacity planning

- Transmission network analysis and planning

- Reliability evaluations

- Power system optimization

- Power system interconnection

List of Proposal Sent to SEC by KFUPM in September 2002.

| Proposal Title | Proposal No. | SEC No. |
| --- | --- | --- |
| Study of Grid Connected Wind Farm | CER2251 | S0202 |
| Wind Energy for Remote Villages | CER2252 | S0102 |
| Environmental Effect on Polymer Insulators Properties | CER2254 | S0402 |
| Automatic Meter reading (AMR) Systems: Perspectives on Procurement Contracting | CER2257 | S0702 |
| Power Quality Standards | CER2255 | S0502 |
| Voltage Unbalance: Causes, Effects and Mitigation Techniques | CER2256 | S0602 |
| Utilization of Peak And Off-Peak Electricity Prices | CER2259 | D0202 |
| Exposure Surveys to Identify High-Exposure Scenarios of EMF | CER2258 | D0402 |
| Integrated Economy-Security Assessment of Power Systems | CER2253 | S0302 |
| Electric and Magnetic Field Guideline Evaluation and Magnetic Field Exposures for Live-Line Workers | CER2260 | D0302 |
| Energy Market Profile for Major Consuming Sectors | CEMS2223 | D0102 |

List of Proposal Sent to SEC by Energy Systems Section in October 2003.

| Proposal Title | Proposal No. | SEC No. |
| --- | --- | --- |
| Overhead Line 13.8 – 33 kV Amelioration | CER2281 | S0603 |
| Demand Forecast for Distribution Network | CER2282 | S0703 |
| Grounding and Bonding Procedures and Requirements in Distribution Network | CER2283 | S0803 |
| Distribution Automation Systems | CER2284 | S0903 |
| Cold Inrush Current in Distribution Network | CER2285 | S1103 |
| Demand Side Management | CER2286 | D0103 |

Saudi Telecom Company (STC)

- Wireless Mesh Networks

- Network Simulation Tools

- Smart Antennas for Fixed Wireless Systems

- Forecast Modeling

- Power Conservation

- Study on Air-Conditioning Compressor problems

SABIC

- Polyolefins

- Basic Petrochemicals

- Speciality chemicals

- Metals

SWCC

- Novel Desalination Technologies

- Novel Scale Control Chemicals

- Materials and Corrosion

- Performance Evaluation and Efficiency Improvements

- Maintenance

- Process development and optimization

Appendix D

Input from KACST S & T plan and Ministry of Higher Education

National Policy for Sciences and Technology by KACST:

Selection of Main Tenants & Objectives:

- Services to unified and sustainable developments.

- Active and effective participations in the development of human civilization.

- Reinforcement of all forms of scientific and technological cooperation with international institutions, so as to keep the Kingdom institutions current on new developments in respective fields of science and technology.

Basic Strategies:

### The policy has set ten basic strategies to achieve the objective of the national policy. The respective ten strategies have been designed to be conducted through itemized policies including:

### Creating mechanisms to encourage the cooperation among all parties involved in the developmental processes of sciences, technology, and innovation.

### Encouraging the private sector to undertake leading and effective role in processes needed for developments in sciences and technology.

### Directing scientific research to increase competitiveness of oil, gas, and petrochemical industries and directing scientific R&D to ensure water security.

### Support to scientific research to ensure sustainable developments through protecting the environments and search for new natural resources.

### Special support to scientific research on new frontiers on electronics, communications and information technology.

### Monitoring of new frontiers of scientific developments that are likely to have strong impacts on the national economy.

### Reinforcement of utilization of international programs and subsidies for the benefit of new developments in sciences, technology and innovations.

### Adopting national programs to start and develop national technologies with supporting laboratories.

### Creating the scientific habitat that is suitable to encourage individual innovations and initiatives, and creating the mechanisms to attract and retain innovative minds to work in these R&D centers.

### Creating the mechanisms to make most efficient utilization of mutual agreements with scientifically and technologically advanced countries and institutions.

### Encouraging and supporting scientific and technological cooperation among individual researchers and research groups from within the kingdom and those abroad.

### Encouraging strategic alliance among national Universities and Research Centers and their counterparts abroad.

Summary of Explorative Studies:

A total of explorative studies have been prepared by the department of planning and follow-up at KACST-Riyadh. The outcome of each study emphasizes the following three basic issues:

  - National trends.

  - Status quo in the Kingdom.

  - Prospects for new developments.

The following Table will itemize each study and some of the key issues that are deemed valuable to developing strategic alliances for science and technology at KFUPM with selected educational, research, and/or industrial organization.

| Subject of explorative study | Key Issues for Strategic Alliance |
| --- | --- |
| Explorations, refining, and utilization of oil, gas and minerals | Needs for alliances with international companies. Privatization of some sectors of the oil industry. Opportunities for academic, research and scientific institutions to expand their cooperation in servicing the oil industry in the kingdom. |
| Petrochemical industries | The strategic importance of the petrochemical industries of to the kingdom requires supporting and developing all research topics related to these industries. Engineering schools must develop their curricula to meet the market demands for these industries. Centers for R & D related to these industries must be supported with advanced technologies and manpower. |
| Information and communications technologies | Needs to improve performance of all national sectors (industrial; government; trade; cultural) and increase job opportunities. The technologies are promising to diversify the economic base in the kingdom Needs to stay current with international developments and participating in such developments through various strategies including establishments of technology incubators. |
| Electronics industries | The industries have three fundamental implications: i) security; ii) developing new industries and/or products; and iii) cultural influences on humans at large. Needs of national and international alliances to improve the kingdom capabilities for training new generations of maintenance engineers. Needs for strategic alliances with vocational institutes in the kingdom or abroad (e.g South Korea; Germany; Japan) to graduate new generation of competent technicians who would be invaluable at times of diminishing resources and when maintenance become a national priority. |
| Aerospace & aviation | The needs for expansions in relevant industries and services like launching satellite require strategic alliances with KACST and other international organizations (such as NASA-USA) to ensure national seeding of the technologies. Establishments of professional societies that will help elevate the public awareness of advanced technologies. Involving the private sectors in developing the relevant advanced technologies through R&D programs. |
| New materials | Nanotechnologies are promising tools to solve complex problems such as pollution and famine. Production of purified aluminum in commercial quantities by using improved Bayer's method. Production of polymer materials and using it in various industrial (such as the car industries) and communications sectors instead of conventional materials. Strategic alliances with SABIC for these ends is one of the most promising fronts of strategic alliances through R&D projects. |
| Bio-technology | Utilization of biotechnologies to protect the environment, to produce energy, and/or improve methods of agriculture. Using bio-technologies to solve new and emerging problems associated with developments such all forms of waste that result from human and industrial processes. Using the technologies to produce new sources of energies such as H2-gas. |
| Agriculture and food | Producing new produces that are tolerant of high salinity at harsh climates. New technologies for agriculture on mountainous regions of the kingdom. Developing new technologies for lengthy storage of consumable goods. Utilizing the relative advantages of climatic conditions to produce certain types of agriculture products. |
| Building & construction | Needs for specialized R&D centers. Needs for more training and proper technical-law enforcement. Needs for more specialized societies and expanding their roles to elevate and protect the welfare of the society. Need to take active role in developing a more genuine national building codes. Needs to perform more scientific research to solve national problems relate to building and construction such as buildings deterioration due to corrosion, improper utilization of structures systems, etc. Needs for strategic alliances to develop materials that are more suitable the harsh environment that prevails in the kingdom. |
| Energy | Needs to have new strategic alliances to develop new technologies for storing and utilization of the available (but not utilized) solar energy. Utilizing the small-scale nuclear energy technology for water desalination by interfacing the reverse osmosis process technology with a small-scale plant for the production of light water. Due to the vital importance of waters for national security, this may require strategic alliances with advanced specialized R&D centers in western Europe, USA, and/or Japan. |
| Health & medicine | Needs for strategic studies to optimal utilization (and/or recycling) of available equipments to maximize economic returns. Needs for specialized studies through strategic alliances with MOH in the kingdom to increase the capabilities of specialized employees to perform scientific research. Utilization of R&D tools to elevate the pharmaceutical industry and reshape it from a transformative process to a creative industry. |
| Transportation | Needs for R&D studies on technologies for vehicles manufacturing, safety, and utilization. Needs for strategic alliances for advanced research to develop engineering design specifications for the structural designs and management of roads and developing more durable materials for road-pavements. Needs for strategic alliances with reputable international transportation companies to develop new modes of mass transit (e.g. affordable, organized, and dependable inter-city and intra-city modes of transportation) to cope with the fast growth in population and the intensive demands on the current transportation system. Needs to develop and utilize suitable modes marine-transportation systems. Needs for R&D studies to develop the technologies of smart roads. |
| Education | Needs for studies to develop the educational systems (organization; procedures & technologies; and policies) in the kingdom Needs for refined studies to reshape the technical vocational institutes through strategic alliances with advanced countries such as Japan utilizing the mutually signed agreements between the Kingdom and Japan. Utilizing of national agreements with other advanced countries (such as France) to redesigns curricula of community colleges to meet the market demands on new generations of specialists in applied fields such as computer technologies and application, accounting and marketing and opening branches all over the kingdom away from the major cities with strategic alliances with the private sector. |
| Environment | Needs for specialized centers on specific environmental issues that will develop data banks and have the capabilities for analysis and utilization of such data. Needs for more advanced studies to monitor indices of environmental changes. Needs for more advanced research studies and strategic alliances on environmental issues including eradication of pollutants (e.g. solid waste management technologies) and pollution sources and transfer of clean technologies. |
| Management sciences | Needs for R&D studies and strategic alliances on the management of education and management technologies in order to increase the competitiveness of the kingdom within the demanding world economies. Needs for new studies to expand the role of the private sector in the privatization of education for the optimal utilization of human and physical resources in the kingdom including the utilization of the available infrastructure of current well-equipped Universities (e.g. reshaping KFUPM policies to allow tuition-based education of foreign students) Expanding the role of private sector in the management and scientific and education activities and patents for scientists. This may help overcome the illusive barriers between the institutions of higher learning, the private industrial section and the society at large, and may even lead the private sector to participate effectively and independently in the industrial development in the nation. |
| Kingdom international cooperation on sciences and technologies | Needs to make refined studies for the best utilization of currently 39-signed agreements between the Kingdom and other countries (including: 15 agreements with advanced countries; 7 agreements with developing countries; 8 agreements with Islamic and Arabic countries; 9 agreements with Arabic countries). Needs for more strategic alliances on the regional level on technological and scientific issues of common interest (e.g. water desalination technologies; oil and gas industries; petrochemical and polymer-production industries). This will help the kingdom and the region have the competitive edge within the world trade organization (WTO). Expanding the role of national institutions of higher learning (e.g Universities; colleges; R&D centers) to participate in the process of cooperation with other partners (local; regional; international) on issues of scientific and technological endeavors, and empowering/encouraging with appropriate incentives (and with minimum bureaucratic hurdles) the roles and initiatives of individual faculty at the institutions of higher learning. Needs for strategic alliances on issues of scientific research, education and students' training, exchange programs, and R&D technologies, between local Universities and reputable international counter-parts (e.g. in USA; Europe & UK; France; Japan; South Korea; China). |
| Societal impact of sciences and technology till the year 2020 | Needs for studies to elevate the societal awareness of the impacts of globalization of the economical practices in the kingdom (e.g. liberation of economy, etc.) on all societal activities including societal, cultural, scientific, and technological, and investments impacts. Needs for swift paradigm shifts on the t current procedure and philosophies on R & D and innovations and emphasis on applied research in research centers, and emphasizing the importance of innovative industries through multi-faceted and multi-national strategic alliances Utilization of R&D tools to elevate the pharmaceutical industry and reshape it from a transformative process to a creative industry. Needs for more refined and advanced studies on optimal utilization of national resources (e.g. oil; gas; minerals), and developing new methods to increase the added values for the national products including petrochemical-based products. |

Kingdom of Saudi Arabia

Comprehensive National Plan for Science & Technology

Ministry of Higher Education

List of Programs and Research Projects Project Duration 4 years: from 2007 to 2010

| Name of Project | Budget (million SR) | Participants |
| --- | --- | --- |
| Advanced and Strategic Technologies |
| Research on Space and aerospace | 90 | KAAU, KSU, KFUPM, KACST, MOCI, PS |
| Research on Desalination & Water Treatment | 35 | KAAU, KSU, KFUPM, SWCC KACST, MOCI, PS |
| Research on Petroleum & Gas | 56 | KAAU, KSU, KFUPM, MOPM, KACST, PS |
| Research on Environment Protection | 48 | KFUPM, KAAU, PME, MOCI, PS |
| Research on Petrochemicals | 75 | KSU, KACST, PS, SABIC |
| Research on Advanced Materials | 51 | KAAU, KSU, KFUPM, KACST, PS |
| Biotechnology & Genetic Engineering | 51 | Univs, KACST, National Research Centers, KFSH&RS, PS |
| Treatment, Prevention and Pharmaceuticals | 30 | KSU, MOH, KFSH&RS, KACST |
| Research on Food Production | 20 | MOAgri, KFU, QU, KACST, PS, IO |
| Electronics, Communications & Light | 80 | KFUPM, KSU, KAAU, KACST, MOCI, PS |
| Research and Development Capabilities |
| Establish Cooperative Research Center | 20 | KACST, PS |
| Study to Enhance University Research Center Capabilities | 5 | KACST, Government Agencies, PS |
| Science, Technology and Community |
| Establish Bibliographic Database for University Theses | 5 | KFCRIS, Univs, KFNL, PS |
| Human, Scientific, and Technology Resources |
| Graduate Studies in the Gifted | 7 | MOE, Vocational Training Inst, KAAGifted, PS |
| Establish Teaching Courses in Innovation and Inventions | 16 | MOE, Vocational Training Inst, KAAGifted, PS |
| Establish and support Scientific Clubs | 38 | KAAGifted, KACST, MOE, PS |

1/2

| for Innovation and Inventions |
| --- |
| Free Innovation Approaches | 12 | PS, SAGIA, Industrial Cities Org. |
| Establish Three Higher Centers of Excellence | 626 | KACST, MODA, National Research Centers, PS |
| Graduate Studies in Strategic and Advance Technologies | 60 | KACST, National Research Centers, PS |
| Open New Colleges & Departments in Strategic & Bio fields | 170 | KACST, National Research Centers, Vocational Training Inst, Military Sectors |
| Training Science and Technology Students | 59 | Government agencies, PS, Vocational Training Inst |
| Scientific, Technology and Innovation Policies |
| Policies of Professional Scientific Societies | 0.834 | KACST, MOCI, Vocational Training Inst, Large Companies, Commerce Chambers |
| Structural Organization for Science, Technology and Innovation |
| Establish Science and Technology Unit | 3 | KACST |
| GRAND TOTAL | 1,557.834 |

KACST

List of Programs and Research Projects Project Duration 5 years: from 2006 to 2010

| Name of Project | Budget (million SR) | Participants |
| --- | --- | --- |
| Technology Development & Transfer |
| Establish Five Technology Incubators at Universities | 30 | MOHE, MOCI, Commerce Chambers |
| Establish Five Centers of Research Excellence at Universities | 75 | MOHE, National Research Centers, PS |

Abbreviations:

MOCI= Ministry of Commerce & Industry; PS= Private Sector, Univs= Universities, MOE= Ministry of Education, IO= Intl. Organizations; MODA= Ministry of Defense & Aviation, MOHE= Ministry of Higher Education; KFCRIS = King Faisal Center for Research & Islamic Studies, MOAgri = Ministry of Agriculture;

Shaded Rows= No Direct Involvement of KFUPM

Appendix E

Feedback from Various KFUPM Departments and Faculty for Proposed Institutions & Consortia

| College | Departments | Number of Feedbacks | Proposed Institutions | Proposed Consortia |
| --- | --- | --- | --- | --- |
| Engineering Sciences & Applied Engineering | Civil Engineering | 1 | National: KACST Regional: Structural Health Monitoring & Control Int.: Concrete Research Institute | Structural Health Monitroing & Control; U. Ohio, Stanford U., U. California at L.A. and KFUPM Structural Designs of RC Structures for Durability; U. Northwestern (USA), U. Glasgow (Scotland-UK) and KFUPM KFUPM |
|  | Chemical Engineering | 2 | National: KSU Regional: Abu Dhabi Petroleum Institute Int.: University of waterloo | Polymers: KFUPM, University of Waterloo (Canada); University of Minho (Portugal) |
|  | Aerospace Engineering | 1 | National: King Abdel Aziz Univ. Regional: Egypt (Cairo University) Int.: Malysia (Islamic University), Univ. Maryland, and Georgia Tech, MIT, Stanford Univ |  |
|  | Petroleum Engineering | 1 | National: Schlumberger's Dhahran Carbonate Research Center Regional: Kuwait Institute for Scientific Research Int.: Stanford University |  |
|  | Electrical Engineering |  | National: Regional: Int.: |  |
|  | Mechanical Engineering |  | National: Regional: Int.: |  |
| Industrial Management | Management & Marketing |  | National: Chambers of commerce, ministry of industry and other universities Regional: Int.: top schools in USA |  |
| Computer Science & Computer Engineering | Computer Engineering | 2 | National: KACST King Saud University, King Abdulaziz University Regional: University of Sharjah / Hashem University, Kuwait University Int.: University of Florida; Virginia Tech., De Montfort University (UK) | 1. Cryptography Hardware; Oregon State University 2. Networking; Cisco Systems |
|  | Systems Engineering | 1 | National: Regional: Int.: International centers of maintenance research such as the one in the University of Toronto. |  |
|  | Information & computer Sciences | 3 | National: KING Abdul AZiz Univ; KACST; Artificial neural networks in Petroleum engineering, King Saud University Regional: Computational Algorithms, Mansoura University, Egypt Int.: 1. Washington University,St. Louis,MO 2. Virginia Tech 3. Carnigi Melun Univ. CMU 4. University of California, UCLA, UC Berkely 5. USC 6. Gorgia Tech 7. McGill Univ 8. Waterloo Univ. 9. Iowa State University | Bioinformatics, Nanotechnology Iowa State University Computational Intelligence and Machine Learning, Data Mining and pattern recognition ; Cornell University |
| Sciences | Mathematical Sciences | 1 | National: Regional: Int.: 1. Faculty of Mathematics, Univ of Waterloo, Canada 2. National University of Sciences and Technology, Rawalpindi, Pakistan |  |
|  | Chemistry | 1 | National: KACST, King Saud, King Abdulaziz Regional: Universities in Qatar, Kuwait, UAE, Oman ad Bahrain Int.: Univesity of Vienna |  |
|  | Physics | 2 | National: KSU; KACST, SABIC; Saudi Aramco Regional: SAFAT, Kuwait, Pakistan atomic energy commision labs, Quid-e Azam Int.: 1. University Islamabad, GIK Topi, Pakistan, 2. Iranian Atomic Energy commission labs, 3. Syrian atomic energy commission labs 4. Max plank Institute, Garching, Germany, MIT,USA -Stanford research institute,USA, CALTECH,USA , CSIRO llbas Sydney, Australia | Nano Science U. of Illinois at Urbana-Champain, USA |
|  | Earth Sciences | 2 | National: Saudi Geological Survey Saudi Aramco Regional: Sabanci University UAE University, Al-Ain; Kuwait Institute for scientific research, Kuwait Sultan Qaboos University, Oman; Int.: CALTEC, MIT, UCLA University of Calgary, Canada (Prof. Stewart), University of Arizona (Colleage of Hydrology and Water resources), UNAM, Mexico City, Geology Punjab University, Lahore, Pakistan. | Earthquake Forecasting; UCLA Seismology &Rock Physics; Edinburgh University Active Fault Research; Geological Survey of Japan Ground Motion; Carleton University water resources; university of Arizona, Tuscan Geostatistics and geologic modeling; University of South Carolina seismic exploration; Stanford university, Rice, Univ. of Houston IsotopeGeology,MIneralogy Caltech,Pasadena,USA JasonSaleeby;Rossman, Geochemistry RoyalHollowayUniversityof London,UK. J.N.Walsh, Michael Thirlwall. Microprobe Analysis,volcanic,rocks; GeologyInstitut,Bern,Switzerland Edwin, Gnoss hydrogeology and water resources: University of Arizona, Princeton university and KFUPM |
|  | Islamic & Arabic Studies |  | National: All Saudi Universities Regional: King Mohd 5th University, Morocco. Int.: Duram, UK | 1. Islamic Studuis: Saudi Universities 2. Profession Ethics: International Islamic University Malaysia 3. Finaucial Transactions: Islamic Commettees in Banks Saudi Arabia 4. Terminologis: King Mohd 5th University Morocco 5. Islamic Civilization: Ledin University Holland 6. Commncation Skills: International Islamic University Malaysia. 7. Islamic Studies: East Studies Islamic Institution 8. Islamic Civilization: Ledin University, Holland. |
| Environmental Design | CER |  | National: Regional: Int.: |  |
| Research Institute | Center for Engineering Research. | 2 | National: PME; KSU; KACST Regional: KISR, University of Bahrain; Building Research Institute, Egypt Int.: 1. University of Waterloo 2. Hydro Quebec’s Research Institute 3.Electric Power Research Institute (EPRI) 4. China Electric Power Research Institute 5. University of New South Wales, Japan, BP Solar, GE Wind, NORDEX- 6. Sherbooke University 7. University of Toronto 8. University of New Brunswick 9. University of California, Berkeley 10. Purdue University 11. University of Leeds, UK 12. Sheffield University, UK 13. University of Dundee, UK | 1. High Voltage, Cable testing, Insulators, Material ; Characterization, Power System Modeling; University of Waterloo; Hydro Quebec’s Research Institute and KFUPM 2. Power Quality, energy conservation, Energy Management; Electric Power Research Institute (EPRI) and KFUPM China Electric Power Research Institute 3. Corrosion: KACST, Universities, Industries 4. Life Assessment of Mechanical Components Industries, Mechanical Solutions USA. |
|  | Center for petrochemicals Research | 2 | National: Saudi Aramco, SABIC, KACST, Ministry of Petroleum, KSU Regional: MEDRC; KISR, KNPC, ADNOC, APICORP Int.: 1. UNESCO Center for membrane Sci, UNSW, Australia; 2. OWRT, USA 3. SHELL, EXXONMOBIL, Japan Petroleum Institute, Tsukuba Science City; British Petroleum 4. Integration of Petroleum Refining and Petrochemicals Industry: KFUPM; Saudi Aramco; JCCP; JPI; Shell International; IFP | 1. Membrane Technology for desalination, KFUPM, SWCC, Saudi Aramco, UNSW; KFUPM, SWCC, Saudi Aramco, 2. Chemicals to prevent oilfield scaling, KFUPM, Saudi Aramco, Rice University |

Appendix F

List of Universities KFUPM has agreement currently with duration and scope

| Country | Institution | Starting Date (Duration for 10 years) | Scope |
| --- | --- | --- | --- |
| USA |
| USA | University of Michigan | 26.5.1999 | Wide-ranging and comprehensively covering almost all areas of education, Research, technology, training, language learning, visits, students, publications, sabbatical , information, etc (No implementation scheme) |
| USA | Northwestern University | 27.5.1999 |  |
| USA | University of Arkansas | 28.5.1999 |  |
| USA | California State University | 01.6.1999 |  |
| USA | California State University System | 01.6.1999 |  |
| USA | University of California | 03.6.1999 |  |
| Canada |
| Canada | University of British Columbia | 04.6.1999 | Wide-ranging and comprehensively covering almost all areas of education, Research, technology, training, language learning, visits, students, publications, sabbatical, information, etc (No implementation scheme) |
| Canada | British Columbia Inst of Technology | 05.6.1999 |  |
| Canada | University of Victoria | 05.6.1999 |  |
| Canada | University of Calgary | 06.6.1999 |  |
| Canada | University of Manitoba | 06.6.1999 |  |
| Canada | Northern Alberta Institute of Technology | 06.6.1999 |  |
| Canada | University of Toronto | 07.6.1999 |  |
| Canada | Seneca College of Applied Arts & Technology | 07.6.1999 |  |
| Canada | Ryerson Polytechnic University | 07.6.1999 |  |
| Canada | York University | 07.6.1999 | Wide-ranging and comprehensively covering almost all areas of education, Research, technology, training, language learning, visits, students, publications, sabbatical, information, etc (No implementation scheme) |
| Canada | McMaster University | 07.6.1999 |  |
| Canada | University of Waterloo | 08.6.1999 |  |
| Canada | University of Ottawa | 09.6.1999 |  |
| Canada | Alogonquin College of Applied Arts and Technology | 09.6.1999 |  |
| Canada | Queen’s University | 09.6.1999 |  |
| Canada | Dalhousie University | 09.6.1999 |  |
| Canada | Concordia University | 11.6.1999 |  |
| Canada | Southern Alberta Inst. of Technology | 06.6.1999 |  |
| Canada | Royal Institution for the Advancement of Learning (McGill University) | 11.6.1999 |  |
| EUROPE |
| France* | University of Rouen | 22.4.2002 | Wide-ranging and comprehensively covering almost all areas of education, Research, technology, training, language learning, visits, students, publications, sabbatical, information, etc (No implementation scheme) |
| France* | University of Jean Moulin Lyon | 22.4.2002 |  |
| Asia |
| 29.Japan* | Waseda University | 15.10.2002 | Visits, student exchange, academic publications, etc |