TEM 11th LESSONS LEARNED

- Registration process shall be revised:

  - Registering names shall be forwarded to the registration committee directly (not Saudi Aramco site);

  - Improve follow up with Saudi Aramco Attendees (non-IT in particular)

  - Registration for courses shall be handled by the provider (separate from registration on conference)

  - Register Saudi Aramco delegates one day before the conference.

  - Continuously check number of on-line registration (about 40% registered one day before the conference)

  - Need a unified list of people registered (upon to the night before) as I saw about 4 or 5 lists around the registration area?

- Develop a procedure for the amount to be deducted from the course provider.

- Employ freelance supporting staff

  - Secretary

  - Web master

  - Accountant

- Develop a procedure for obtaining speaker’s visas

- Plaques should be tagged on the cover to eliminate confusion, organize better next time.

- Open the event for participation of individuals.  Limit invited speakers to one per session.

- Continue the tradition of having a student session.

- Student Session:

  - Develop rules for the competition for student projects.

  - Improve students’ projects selection for the event.

- Add vendor’s exhibition

- Reception Area for VIP/speakers

  - Need for VIP reception area for invited speakers to come directly to with a large sign showing the reception desk for VIP/invited speakers

  - Have nice reception area for gusts, speakers for the purpose of networking.

- Need 1 newsletter to be ready for distribution at start of day one mentioning any changes, nice welcome etc..

- Need a booth for the different societies we have so we can attract new members

- Need the coupon for bag which should be numbered so we know how much are remaining at any moment

- Need the area for distributing bag next to the registration desk

- Need a PC with project ability so we can show announcements, changes to the program, etc....

- Need to organize a special meeting with the invited speakers, to get their feedback and make them feel that from now they are part of this event.

- Microsoft keynote speech was of Ad type (marketing).  It should not be like that.  This needs to be discussed in details.

- Technical Program

  - In panel discussion, it is a panel for discussion so no need for lengthy presentations and lectures.

  - Avoid the 5 minutes break before the keynote speech (ply it differently).

  - Technical program, though good, was too short (20minutes), particularly for guest speakers.

  - Building and rooms very small (maybe require 3 parallel session if space limited)

  - Some technical papers were very poor (better scanning next time).

  - Improve attraction of good foreign speakers.

- Publicity could have been better (within and out with KFUPM)

- Get all volunteering students (helping in the event) to wear IEEE (event) T-shirts to be easily recognized.

- Assign delegated students for each room (help in handling microphones for questions, water for speakers, etc.)