IMPROVEMENT OF RESEARCH ADMINISTRATION

Sadiq M. Sait

Aim:

Establish effective research administration structure, policies and procedures.

Objectives:

- Review current research administration, policies and procedures at KFUPM and best practices at international universities

- Promote conducive research culture and enhance research environment

- Develop strategies to recruit competent graduate students and involve University students (of all levels) in research activities

- Develop appropriate integrated research administration structure, policies and procedures.

Actions:

Task 1: Internal Assessment of Existing Research Administration

- Evaluate the administration structure of academic and contract research.

- Assess the current policies and procedures for academic and contract research

- Review existing research culture and identify strengths and weaknesses

- Identify strengths and weaknesses of the existing research management policies and procedures.

Task 2: Review of International Research Administration Practices

- Review the management structure of academic and contract research of selected international universities and research organizations

- Review the policies and procedures and research culture of selected international universities and research organizations

- Compare selected international models with the existing KFUPM research administration model

Task 3: Develop the Research Administration Structure, Policies, and Procedures

- Establish the most appropriate administration structure to conduct  research at KFUPM integrating all departments and research center

- Develop policies and procedures to improve overall efficiency and establish appropriate research culture

Time Frame:

| Task | Time Frame (man-months) |
| --- | --- |
| Task 1: Internal Assessment | 4 |
| Task 2: Review of international research administration | 4 |
| Task 3: Develop Research Management Structure, Policies, and Procedures | 2 |
| Total | 10 |

Key Measures:

- Increased efficiency of research work

- Satisfaction of researchers and clients

- Number of research groups

- Multidisciplinary research programs

Resources:

- Internal data

- Data from international universities

Responsibility for implementation:

- Vice Rector for Graduate Studies and Scientific Research

- Vice Rector for Applied Research

- Dean

- Chairman

- Center Director