# CEN 593

# ENGINEERING MANAGEMENT

Introduction

One of the most important functions of project controls is to accurately evaluate the physical progress of engineering, procurement and construction activities.

Physical progress is the primary factor in:

- Determining progress payments due to the contractor.

- Evaluating the impact of changes, interferences and delays.

- Measuring the contractor's performance to his plan.

- Projecting final costs and facility turnover dates.

The following guidelines offer an objective method of determining physical progress for each phase of a project from start of design to project completion.

Engineering

Physical progress for the engineering phase of a project consists of three levels of indenture as follows:

- Progress by drawing

- Progress by discipline

- Total engineering progress

Estimate

Prior to implementing a system for progress evaluation an estimate must be developed for both manhours and quantities of drawings for each engineering discipline. For these guidelines we will assume the estimate shown in Table 1 next page.

Progress Evaluation

Actual physical progress is measured against the drawings only. The progress measurement for each engineering discipline and for the total engineering effort is a function of the progress against each individual drawing.

| DISCIPLINE | ESTIMATED DRAWINGS | BUDGETED MANHOURS | DISCIPLINE WEIGHTED (%) |
| --- | --- | --- | --- |
| CIVIL | 20 | 1,250 | 8.3 |
| ARCHITECTURAL | 35 | 2,500 | 16.7 |
| STRUCTURAL | 20 | 1,250 | 8.3 |
| MECHANICAL | 20 | 1,500 | 10.0 |
| PIPING | 50 | 4,000 | 26.7 |
| ELECTRICAL | 40 | 3,000 | 20.0 |
| INSTRUMENTS | 15 | 1,500 | 10.0 |
| TOTAL ENGINEERING | 200 | 15,000 | 100 |

TABLE 1

To objectively determine the physical progress against each drawing a series of milestones are established to give credit for incremental work accomplished. The following is an example of typical drawing milestones and their related values to the completed drawing:

Drawing Milestones

Start draft  (20%) Layout and design completed and actual line work visible. Rough draft of specification is completed ready for draft typing.

Draft complete  (65%) Drawing has been completed by drafting, checked by chief draftsman, and issued to engineering for checking. Specification is ready for checking.

Office check  (80%) Engineering has reviewed the drawing and pertinent corrections has been incorporated by draftsmen and  engineers.

Owner review  (85%)  Drawing and specification have been reviewed by the owner and returned with comments.

Final draft  (90%) All engineering  and owner comments have been incorporated and drawing and specification have been issued to owner for approval.

Approval with holds   (95%)  Drawing and specification have been  approved by owner and are ready to be issued for construction with the exception that some portion(s) of the drawing has "holds", waiting for final resolution.

Final owner  Approval (100%) Drawing and specification have been approved by the owner and they are ready to be issued as approved for construction with no "holds".

In order to control the drawing process and effectively monitor the accomplishment of the above-mentioned milestones, a drawing control log should be maintained to record the accomplishment of each milestone and identify the location of each in-process drawing.

Progress by Discipline

Now that the estimated number of drawings for each engineering discipline has been established and the drawing milestones have been defined and assigned a weighted value, the physical progress for each discipline can be evaluated.

For example, assume the work status shown in Table 2 for the 50 piping drawings referenced in Table 1.

| MILESTONE | DRAWS.IN MILESTONE | PIPE DRAWINGS | MILESTONE VALUE | DISCIPLINE % COMPL. |
| --- | --- | --- | --- | --- |
| Start Draft | 10 | 50 | 20 | 4.0 |
| Draft Comple. | 5 | 50 | 65 | 6.5 |
| Office Check | 5 | 50 | 80 | 8.0 |
| Owner Review | 5 | 50 | 85 | 8.5 |
| Final Draft | 5 | 50 | 90 | 9.0 |
| APPR.W/H | 5 | 50 | 95 | 9.5 |
| Final Approv. | 10 | 50 | 100 | 20.0 |
| Piping Progr. |  |  |  | 65.5 |

TABLE 2

The progress for each of the other engineering disciplines could be calculated in the same manner.

Total Engineering Progress

As each drawing milestone represents a portion of the total drawing, so does each engineering discipline represent a portion of the total engineering effort.

Because certain disciplines may require more manhours per drawing than others, depending on the nature and complexity of the project, the weighted value of each discipline is determined by the engineering manhours budgeted to the project

To calculate total engineering physical progress, the percentage of drawing completion for each discipline, would be multiplied by that discipline's weighted value. The product of this calculation would be the discipline's contribution to total engineering progress.

For example:

The piping discipline, was calculated to be 65.5% completed. Let us assume the percentages of completion for the remaining disciplines and the total engineering physical progress would be calculated as shown on Table 3.

| DISCIPLINE | PERCENT COMPLETE | WEIGHTED VALUE | PROJECT CONTRIBUT. |
| --- | --- | --- | --- |
| CIVIL | 90 | 8.3 | 7.5 |
| ARCHITECTURAL | 70 | 16.7 | 11.7 |
| STRUCTURAL | 80 | 8.3 | 6.6 |
| MECHANICAL | 75 | 10.0 | 7.5 |
| PIPING | 65.5 | 26.7 | 17.4 |
| ELECTRICAL | 60 | 20.0 | 12.0 |
| INSTRUMENTS | 50 | 10.0 | 5.0 |
| ENG. PROGRESS |  |  | 67.7 |

TABLE 3

PROCUREMENT MEASUREMENT

Normally for a major project, the procurement of long lead technical equipment and materials is a function of the engineering effort and it is included in the Engineering budget as a separated item.

The procurement effort consist of three major functions as follows:

- Material take-offs

- Purchase requisitions

- Purchase orders

To measure physical progress of the procurement effort, each of the three functions should be weighted as a percentage of the total procurement effort. This weight factor should be based on the budgeted manhours for each function relative to the budgeted manhours for the total procurement effort. (see Table 4)

| FUNCTIONS | ESTIMATED QUANTITIES | ESTIMATED MANHOURS | FUNCTION % WEIGHTED VALUE |
| --- | --- | --- | --- |
| MAT. TAKE-OFF | 150 | 400 | 26.6 |
| PR’s | 200 | 700 | 46.7 |
| PO’s | 100 | 400 | 26.7 |
| Procurement |  |  | 100 |

TABLE 4

Material Take-offs

Physical progress measurement for material takeoffs is based on the estimated number of drawings requiring material takeoffs versus the number of drawings for which takeoffs have been completed.

For example:

The estimated drawings requiring takeoffs = 150

Drawings with takeoffs complete                   =  75

Physical progress would be:     (75/150)(100) =  50%

Purchase Requisitions

Physical progress measurement for purchase requisitions is based on the estimated total number of purchase requisitions versus the number of requisitions approved for purchase.

For example:

The total estimate of Purchase Requisitions    = 200

Purchase Requisition approved for purchase =   50

Physical progress would be:  (50/200)(100)     =  25%

Purchase Orders

Progress should be based on both the quantity of purchase orders placed and the cumulative dollar value of materials shipped from the manufacturer's plant (explanted). The quantity of purchase orders placed will contribute 50 percent progress and the dollar amount of total material value explanted will contribute the remaining 50 percent.

For instance, the purchase order quantity is 100 with 28 purchase orders placed. The total cost of purchase materials is estimated at 50 million dollars and from this amount approximately 1 million dollars of materials has been explanted. Progress would be calculated as follows:

28 PO's placed out of 100   =  0.28( 0.5 )100 = 14%

$ 1 MM of materials explanted out of $50MM   =    0.02 x 0.5 (100)   = 1%

Progress to date for purchase orders:         14 + 1 = 15%

Total Procurement Progress

By evaluating the physical progress of each major procurement function, the total procurement progress can be determined (see Table 5).

| FUNCTIONS | PERCENT COMPLETE | WEIGHTED VALUE | PROCUREMENT CONTRIBUTION |
| --- | --- | --- | --- |
| TAKE-OFFS | 50 | 26.6 | 13.3 |
| PR’s | 25 | 46.7 | 11.7 |
| PO’s | 15 | 26.7 | 4.0 |
| Procurement | Progress |  | 29.0 |

TABLE 5

###### Design and Engineering Overall progress

To evaluate the Design/Engineering overall progress, the value of the engineering effort must be combined with the value of the procurement one. (see Table 6)

|  | BUDGETED MANHOURS | WEIGHT VALUE | % COMP. | PROJECT CONTR. |
| --- | --- | --- | --- | --- |
| ENGINEERING | 15000 | 90.9 | 67.7 | 60.6 |
| PROCUREMENT | 1500 | 9.1 | 29.0 | 2.6 |
| Total Progress | 16500 | 100 |  | 63.2 |

TABLE 6

CONSTRUCTION

There are two basic methods of determining physical progress for the construction phase of a project, they are:

- Intermediate Milestone

- Percentage Complete

The approach to performing the construction phase of a project can vary considerably from one project to another and from one contractor to another. Because of this fact, it is

very important that the activities and/or milestones selected as progress measurement criteria reflect the contractor's approved work plan and schedule.

It is equally important that the estimated manhours to perform these activities be as accurate as possible.

###### Intermediate Milestone Method

The intermediate milestone method gives credit for progress only when a milestone has been completed. This method would apply to small, short term projects (from 3 to 6 months) where cash flow to the contractor would not present a problem. The method is effective to the project team because it requires less surveillance and documentation is totally objective and requires little interpretation.

To calculate progress using the intermediate milestone method, several progress milestones should be identified starting with "mobilization" and ending with "commissioning". Each milestone would be weighted based on the estimated construction manhours required to complete the milestone versus the total construction manhours required to complete the project.

This means that even if the contractor has already started piping and electrical construction, he receives no credit for physical progress until the corresponding milestones are completed.

###### Percentage Complete Method

The percentage complete method is probably the most commonly used form of progress measurement. In this method the activities on the project schedule are weighted by the estimated construction manhours required for each activity versus the total construction manhours required to complete the project.

In the percentage complete method, credit is allowed for incremental work accomplished against each activity based on the activity's estimated percentage of completion. The estimated percentage of completion for an activity can be determined by two methods, as follows:

Credit by units installed:  Using this method of credit, the percentage of completion for each activity is based on the units of work installed (e.g.: cubic yards, tons, linear feet) for the activity versus the total estimated units required for completion.

The number of units actually installed is normally determined or verified by a quantity surveyor, who physically quantifies the units installed, however, cognizant personnel such as the scheduling engineer, project engineer or construction manager could perform this task.

Credit by earned manhours:  This method is applied to activities for which a specific unit of measure, other than manhours earned, would be misleading or difficult to identify. This method also compensates for varying degrees of difficulty in installing similar units, ie.:

a squared foundation requiring 25 cubic yards of concrete would require much less effort than a 5 cubic-yard specially shaped foundation yet, by the "units installed" method, the one squared foundation would receive the same credit as the 5 shaped foundations.

Credit by earned manhours is essentially an estimate of the manhours remaining to complete an activity versus the original activity manhours estimate. This estimate determines "earned manhours".

For instance:

An activity is estimated to require 2000 manhours.

To date, 1500 manhours have been expended performing the activity.

Project personnel estimate that it will require 1000 manhours to complete

the remainder of the activity.

Therefore, the percentage of completion for this activity would be:

2000 M/H original estimate MINUS

1000 M/H estimated remaining

EQUAL : 1000 M/H earned

1000 M/H earned/ 2000 M/H original = 50% complete.

The actual manhours expended are not considered in the calculation of earned manhours. Table7 next page, represents a condensed example of a list of weighted activities.

| MILESTONE | ESTIMATED MANHOURS | WEIGHTED PERCENTAGE |
| --- | --- | --- |
| MOBILIZATION & GRADE | 2000 | 5 |
| FOUNDATION COMPLETE | 4800 | 12 |
| STRUCTURAL STEEL COMPLETE | 3600 | 9 |
| EQUIPMENT ERECTION COMPLETE | 5600 | 14 |
| PIPING COMPLETE | 10000 | 25 |
| ELECTRICAL COMPLETE | 6800 | 17 |
| MECHANICAL COMPLETION | 5200 | 13 |
| COMMISSIONING | 2000 | 5 |
| TOTAL PROJECT VALUE | 40000 | 100 |

TABLE 7

Table 8  represents a sample of the percentage complete progress

measurement method based on the weighted activities listed in Table 7.

| MILESTONE | WEIGHTED PERCENT | PERCENT COMPLETE | PROJECT CONTRIBUTION |
| --- | --- | --- | --- |
| MOBILIZATION & GRADING | 5 | 100 | 5 |
| FOUNDATIONS | 12 | 80 | 9.6 |
| STRUCTURAL STEEL | 9 | 30 | 2.7 |
| EQUIPMENT ERECTION | 14 | 10 | 1.4 |
| TOTAL PHYSICAL PROGRESS |  |  | 18.7 |

TABLE 8

Problem 1

Given the following information, calculate the percentage completion of the engineering effort for the project:

(estimate the budgeted manhours at your discretion)

|  | Estimated Drawings | Budgeted Manhours | Weight Value | % Complete | Project Total |
| --- | --- | --- | --- | --- | --- |
| Civil Engineering | 45 |  |  |  |  |
| Architectural | 23 |  |  |  |  |
| Structural | 28 |  |  |  |  |
| Piping | 35 |  |  |  |  |
| Electrical Engineering | 29 |  |  |  |  |
| Mechanical Engineering | 16 |  |  |  |  |
| Instrumentation | 14 |  |  |  |  |
| TOTAL: |  |  |  |  |  |

### CIVIL ENGINEERING

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start | 20 | 45 | 20 |  |
| Draft Complete | 5 | 45 | 65 |  |
| Office Review | 8 | 45 | 80 |  |
| Owner Check | 2 | 45 | 85 |  |
| Final Draft |  | 45 | 90 |  |
| Approval with Holds |  | 45 | 95 |  |
| Final Approval |  | 45 | 100 |  |

### ARCHITECTURAL

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start | 2 | 23 | 20 |  |
| Draft Complete | 5 | 23 | 65 |  |
| Office Review | 3 | 23 | 80 |  |
| Owner Check | 4 | 23 | 85 |  |
| Final Draft | 2 | 23 | 90 |  |
| Approval with Holds |  | 23 | 95 |  |
| Final Approval |  | 23 | 100 |  |

# STRUCTURAL

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start | 3 | 28 | 20 |  |
| Draft Complete | 4 | 28 | 65 |  |
| Office Review | 5 | 28 | 80 |  |
| Owner Check | 6 | 28 | 85 |  |
| Final Draft | 7 | 28 | 90 |  |
| Approval with Holds |  | 28 | 95 |  |
| Final Approval |  | 28 | 100 |  |

### PIPING

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start | 1 | 35 | 20 |  |
| Draft Complete | 2 | 35 | 65 |  |
| Office Review | 3 | 35 | 80 |  |
| Owner Check |  | 35 | 85 |  |
| Final Draft | 10 | 35 | 90 |  |
| Approval with Holds |  | 35 | 95 |  |
| Final Approval |  | 35 | 100 |  |

### ELECTRICAL ENGINEERING

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start |  | 29 | 20 |  |
| Draft Complete |  | 29 | 65 |  |
| Office Review |  | 29 | 80 |  |
| Owner Check |  | 29 | 85 |  |
| Final Draft |  | 29 | 90 |  |
| Approval with Holds | 29 | 29 | 95 |  |
| Final Approval |  | 29 | 100 |  |

### MECHANICAL ENGINEERING

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start |  | 16 | 20 |  |
| Draft Complete |  | 16 | 65 |  |
| Office Review |  | 16 | 80 |  |
| Owner Check |  | 16 | 85 |  |
| Final Draft |  | 16 | 90 |  |
| Approval with Holds | 16 | 16 | 95 |  |
| Final Approval |  | 16 | 100 |  |

### INSTRUMENTATION

|  | Drawings in Milestone | Total Drawings | Milestone Value | % Complete |
| --- | --- | --- | --- | --- |
| Draft Start |  | 14 | 20 |  |
| Draft Complete |  | 14 | 65 |  |
| Office Review |  | 14 | 80 |  |
| Owner Check |  | 14 | 85 |  |
| Final Draft |  | 14 | 90 |  |
| Approval with Holds |  | 14 | 95 |  |
| Final Approval | 14 | 14 | 100 |  |

100

Problem 2

Given the information in the table below, calculate the percentage completion of the following 700 tons structure:

| Allow Credit | Task | Unit of Measure | Total Quantity | Quantity To date | Earned Tons |
| --- | --- | --- | --- | --- | --- |
| 0.05 | Bolts | Each | 300 | 120 |  |
| 0.40 | Columns | Each | 110 | 56 |  |
| 0.30 | Beams | Each | 600 | 123 |  |
| 0.10 | Girts/rods | Bay | 70 | 24 |  |
| 0.10 | Align | % | 100 | 10 |  |
| 0.05 | Punch List | % | 100 | 5 |  |