# Summary

- Completed literature review and preliminary issues list for Infrastructure and Finance.

- Two task groups, one for Infrastructure & Finance, and the other for IT have been identified.

- Questions for identified issues are being formulated.

- Contact persons from the track team with external study PIs have been named

# Accomplishments

The activities completed in this period are:

|  |  |  | Status |
| --- | --- | --- | --- |
| 1 2 3 4 5 6 | Reviewed of literature on Internet and documents in the DMS system Phone interviews with local experts Visit to Riyadh to meet IT Study meet Meeting with local experts (1 interview completed) Creating hypothesis and identifying key problems in brainstorming sessions (IT and Finance) Creating hypothesis and identifying key problems in brainstorming sessions (Infrastructure) |  | In-Progress In-Progress Completed Completed Completed In Progress |

# Next Period Activities (FROM 13th May 2006 – 24th May 2006)

The planned activities for the next period are:

|  |  |  | Responsibility |
| --- | --- | --- | --- |
| 1 2 3 4 5 | Formulating Questions to be put to the experts Identifying key issues and questions to be presented to international experts Confirming problems and ambitions identified through data, meeting external Calling local experts Visit PIs of external study projects |  | Track Team Track Team Track Team Identified Members Identified Members |

# Deliverable Tracking

|  |  |  | Status |
| --- | --- | --- | --- |
| 1 2 | Problem Definition Presentation to Committee and External experts |  | In progress In preparation |

# Issues & Risks

|  |  | Type/ Severity | Mitigation Strategy | Target Date/ Responsibility |
| --- | --- | --- | --- | --- |
| 1 | Prince Sultan University for his study has not been signed as yet, and therefore it is inappropriate to contact the PI until this is done. | Medium | This must completed soon. | ASAP |